## Oak Meadow Restroom
IFB NO. 22-030 |  |  |  |  | DUE DATE: |  |  | 2022-03-09
BID FORM
for
OAK MEADOWS ON-SITE WASTEWATER TREATMENT SYSTEM AND
RESTROOM RENOVATION PROJECT
* All items complete in place *
NOTICE TO CONTRACTORS: YOU ARE REQUIRED TO USE THIS FORM WHEN SUBMITTING A BID.
Will you accept payment by VISA credit card? |  |  |  |  | YES_______ |  | NO_______
If you accept VISA, is there a cost? |  |  |  |  | YES_______ |  | NO_______
If cost or min/max amount, explain:_______________________________________________
Line | Item | Unit of | Est. | Unit | Extended
No. | Description | Measure | Qty. | Price ($) | Price ($)
1 | Final Design & Permitting | LS | 1
2 | Mobilization | LS | 1
Oak Meadows OWTS
3 | Septic tank, 2000 gal. min. (CIP) | LS | 1
4 | 4" schedule 40 PVC pipe (CIP) (6" under roadway) | LF | 500
5 | Relocate picnic table | LS | 1
6 | Soil Treatment Area 100'x100' (CIP) | LS | 1
Oak Meadows Restroom Renovation
7 | Restroom electrical service | LS | 1
8 | Restroom mechanical & plumbing | LS | 1
9 | Concrete demo and patch | LS | 1
10 | Remove Toilets, Urinals, and Underground Vault | LS | 1
13 | Install new toilet with sensor | EA | 3
14 | Install new urnial with sensor | EA | 1
15 | Install new toilet partitions | LS | 1
16 | Install new hot water heater for restroom | EA | 1
17 | Install new grab bars and dispensers | LS | 1
18 | Install new LED light fixtures in restroom | EA | 8
19 | Paint restroom interior (clean and paint interior including floor) | LS | 1
20 | Paint restroom exterior and replace facia | LS | 1
Add Option No. 1 - Pine Meadows Restroom Connection Pipe
A1 | 4" schedule 40 PVC pipe (CIP) (6" under roadway) | LF | 900
| SUBTOTAL |  | SUBTOTAL |  | =
21 | F/A Minor Contract Revisions | LS | 1 | 20000 | 20000
|  |  | TOTAL PROJECT PRICE |  | $
Number of Calendar Days to completion upon reciept of Notice-to-Proceed: |  |  |  |  | _______ Days
NOTE: Price must be inclusive of (but not limited to) the following: all contractor fees, actual costs, overhead, profit, permits and (if required) performance and payments bond costs.
Our submitted bid consists of a total price, all inclusive of any freight, surcharges, labor, insurance, materials, and any other miscellaneous incidental charges required to perform the services, except taxes as county is tax exempt:
Submitted by:________________________________________________________________ |  |  |  |  | Date: | _________________________________
(Company Name)
Federal ID# / SS#:____________________________________________________________ |  |  |  |  | Email: | _________________________________
Address:____________________________________________________________________ |  |  |  |  | Phone: | _________________________________
City State Zip:________________________________________________________________ |  |  |  |  | Fax: | _________________________________
Authorized
Signature:___________________________________________________________________
Printed Authorized
Signature:___________________________________________________________________